## Slide 1
Smart Industrial Maintenance System - FSE 570 Capstone Status Update 2
Apr 2, 2026 | Arizona State University
✅ Accomplishments & KPIs
0.933 F1
LSTM Failure Predictor
(AUC-ROC: 0.997)
0.937 R²
XGBoost RUL - C-MAPSS
(RMSE: 10.48 cycles)
0.992 C-Index
Bayesian Survival
(90% & 95% CI)
COMPLETED SINCE STATUS UPDATE 1
✔ BCELoss Fix: Sigmoid removed; BCEWithLogitsLoss adopted - LSTM retrained with corrected loss
✔ Simulation Fix: Availability formula corrected; 100-iteration MC rerun with clean health arrays
✔ IMS Bearing Pipeline: NASA IMS vibration dataset added - FFT, RMS, kurtosis, crest factor features
✔ Sol GPU Training: Both C-MAPSS and IMS pipelines trained on ASU Sol Supercomputer GPU
✔ End-to-End Notebook: 1,558-line Jupyter notebook - training, MILP scheduling, simulation, evaluation
✔ Expanded Test Suite: 231 IMS unit tests added (test_ims.py) - extraction, preprocessing, models
📋 Next Tasks - Rolling Action Item List (RAIL)
IMMEDIATE - REPORT WRITING (Apr 2 -> Apr 20)
[Anoushka] Write results section - C-MAPSS model metrics, confusion matrices, RUL prediction plots, anomaly detection examples
[Deva] Write simulation and MILP results - corrected cost-reduction figures, schedule comparison tables, policy benchmarks
[Mohit] Write IMS bearing pipeline section - feature extraction methodology, FFT analysis, bearing degradation results
[Umang] Write discussion section - cross-dataset comparison, model generalization findings, limitations and future work
[Urvansh] Write conclusion and references; compile all sections into final report document; ensure formatting consistency
FINAL STRETCH - PRESENTATION (Apr 21 -> Apr 30)
• Anoushka: Build slides - model results, KPIs; prepare live Streamlit dashboard demo (fleet, risk, MILP, IMS)
• Deva: Build slides - simulation results, MILP scheduler, corrected cost-reduction policy comparison
• Mohit + Umang: Build slides - IMS bearing pipeline, SHAP explainability, cross-dataset analysis and discussion
• Urvansh: Build slides - conclusion and future work; compile final report; coordinate Apr 30 submission
⚠️ Risks, Barriers & Mitigations
RISK REGISTER (Likelihood × Impact)
Anoushka Updated LSTM result figures not yet regenerated after BCELoss fix - report results section blocked
-> Retraining complete; regenerating confusion matrix, AUC, and RUL plots this week before writing
Deva Corrected simulation cost-reduction stats pending final MC rerun - numbers in report could change
-> Clean 100-iteration MC run scheduled this week; figures locked before report freeze Apr 17
Mohit IMS bearing experiment results still being analyzed - cross-dataset comparison not yet finalized
-> IMS evaluation running on Sol this week; results handed to Umang for discussion by Apr 10
Umang Discussion section depends on both C-MAPSS and IMS results being ready - writing blocked until then
-> Drafting structure and conclusions in parallel; will fill in numbers once Mohit's results are in
Urvansh Streamlit Cloud uptime during live demo not guaranteed - outage would break the demo mid-presentation
-> Full local backup on laptop and static screenshots prepared; demo treated as supplementary not critical
📅 Remaining Activities & Approach
FINAL SPRINT (Apr 2 -> Apr 30, 2026)
WEEK 1 - RESULTS & WRITING FOUNDATION (Apr 2 -> Apr 10)
Apr 2 Status Update 2 check-in (today) - 10 pts - Zoom quad chart review with professor
Apr 2–7 Generate all result figures - Updated metrics, RUL plots, SHAP, IMS bearing degradation curves
Apr 7–10 Results + IMS sections drafted - Anoushka, Deva, Mohit writing in parallel
WEEK 2 - REPORT COMPLETION (Apr 11 -> Apr 20)
Apr 11–14 Discussion + conclusion sections - Umang + Urvansh; cross-dataset findings, limitations, future work
Apr 15–17 Full report assembled and cross-reviewed - All members; internal deadline Apr 17
Apr 18–20 Final polish and formatting - Citations, figures, abstract, table of contents
WEEK 3 - PRESENTATION (Apr 21 -> Apr 30)
Apr 21–25 Build presentation slides - Each member owns one section; dashboard demo prep
Apr 27–29 Full rehearsal run-throughs - Time sections; align transitions; practice Q&A
Apr 30 Final Submission (50 pts total) - Capstone Report (30 pts) + Presentation (20 pts)
Team: Anoushka Dighe • Deva Siva Kanth Tavvala • Mohit Kumar Petla • Umang Bid • Urvansh Shah
FSE 570 | Spring 2026 | ASU