## Slide 1
🏭 Smart Industrial Maintenance System
FSE 570 Capstone | Status Update 1 | Arizona State University
✅ Accomplishments & KPIs
▶ Anoushka
0.933
F1-Score
LSTM Predictor
0.937
R² Score
XGBoost RUL
97.4%
Cost ↓
vs. Reactive
COMPLETED MILESTONES
• Dataset: NASA C-MAPSS FD001 downloaded & preprocessed (200+ engineered features)
• LSTM Autoencoder: Trained for anomaly detection; threshold = mean + 3σ, AUC-ROC 0.997
• XGBoost RUL: RMSE 10.48 cycles, R² 0.937 — walk-forward CV validated
• Bayesian Survival: WeibullAFT fitted; C-Index 0.992; 90%/95% credible intervals
• MILP Scheduler: PuLP optimizer — crew capacity + mandatory critical-machine constraints
• Streamlit Dashboard: 5-tab interactive app: fleet overview, risk, schedule, history, context
• Test Suite: 27 unit tests passing across models, optimizer, and preprocessing
📋 Next Tasks & Assignments
▶ Deva Siva Kanth
IMMEDIATE (Week 2–3)
Anoushka
Fix BCELoss double-definition bug in LSTM predictor
Deva
Fix health-array mutation bug in Monte Carlo simulation
Mohit
Vectorize trend-feature polyfit loop (performance bottleneck)
Umang
Integrate SHAP explanations into dashboard Risk tab
Urvansh
Add simulation unit tests (test_simulation.py)
UPCOMING (Week 4–6)
• All: Final report writing & slide polish (parallel effort)
• Anoushka + Deva: Sol Supercomputer training run — full FD001–FD004 datasets
• Mohit + Umang: Multi-dataset benchmarking; hyperparameter sweep
• Urvansh: Dashboard deployment to Streamlit Cloud for live demo
⚠️ Risks, Barriers & Mitigations
▶ Mohit
HIGH
BCELoss bug may have impaired LSTM training; reported F1 needs re-verification
→ Retrain after fix; compare before/after metrics
HIGH
Simulation cost-reduction stats (97.4%) likely inflated due to numpy mutation bug
→ Fix & rerun 100-iteration MC sim; update README
MED
Sol Supercomputer access not yet provisioned; GPU training blocked
→ Professor submitting roster this week; fallback = Colab T4
MED
Feature engineering polyfit loop too slow for full FD001–FD004 scale
→ Vectorize with numpy stride tricks before Sol run
LOW
FD002/FD003/FD004 multi-condition generalization unvalidated
→ Scope to FD001 for final; note as future work
📅 Remaining Activities & Timeline
▶ Umang
W1
W2
W3
W4
W5
W6
W7
W8
Bug Fixes
Feature Eng.
Sol GPU Run
SHAP / XAI
Multi-dataset
Dashboard Polish
Final Report
Final Presentation
NOW
Team: Anoushka Dighe • Deva Siva Kanth Tavvala • Mohit Kumar Petla • Umang Bid • Urvansh Shah
FSE 570 | Spring 2026